## Decision log
Decision log
Maintained by Kumara D.G.K.R.D. (IT24103972) · each decision reviewed by the group
ID | Stage | Decision | Options considered | Chosen option and reason | Evidence | Owner
D01 | Framing | Prediction cut-off | Before lineups / after lineups, before kickoff / in-match | After lineups, before kickoff: uses the real XI while staying a pre-match forecast. | Report §4; canvas box 3 | Kumara
D02 | Framing | Target definition | Exact score / win vs not-win / H-D-A | H / D / A, built from the final score. | Report §2, §7 | Kumara
D03 | Framing | Primary metric | Accuracy / Macro-F1 / log loss | Macro-F1, so the smaller Draw class counts equally; log loss and Brier as support. | Report §16, §18.2 | All
D04 | Data | Data sources | Football-Data.co.uk results and odds only / Kaggle European Soccer Database (the descriptor's Code 9 dataset) + Transfermarkt | Kaggle European Soccer Database (2008-2016; the dataset the descriptor links for Code 9) + Transfermarkt (2016-2026) as a declared supplementary source: only these have lineups and dated player values. | Source notes §1 | Kumara
D05 | Data | How to combine the sources | Join rows / stack rows | Stack: each match comes from one source; same 62-column schema; no time overlap. | Source notes §3; data-engineering notebook Part C | Kumara
D06 | Data | Leagues kept | 11 leagues / 9 leagues | 9 leagues: Switzerland and Poland miss 2016-2023 and Poland lacks player data for 62.6% of matches. | R 01 · C_why_C1_PL1_removed.csv | Kumara
D07 | Data | Which raw tables | All tables / pre-match tables only | Pre-match tables only; appearances and game_events excluded from the dataset (in-match information). | Source notes §2 | Kumara
D08 | Features | Player-quality signal | None / raw values / causal relative index | Causal 0-100 percentile within league and role, from values dated before the match. | Feature log F03; report §10.2 | Jayawardana
D09 | Features | Missing values | Zero-fill / drop rows / NaN + train-only imputation | Keep NaN, median-impute inside the pipeline on training data only; dropping rows tested and did not help. | Preprocessing log P03; report §18.3 | Jayawardana
D10 | Features | Feature strategy | All at once / automatic filter / staged ablation | FS1 → FS4 ablation to answer the research questions directly. | Report §11, §17 | Jayawardana
D11 | Features | Extra features from appearances | Add rest days, discipline, player form / keep FS3 | Keep FS3: best gain +0.004, within noise, and data exist only from 2016. | new_feature_experiment.csv | Jayawardana
D12 | EDA | Train / validation / test split | Random / chronological | Chronological (≤ 2022 / 2023 / ≥ 2024): outcomes drift over seasons (EDA E02-E04). | Report §12; EDA log | Jayamuni
D13 | EDA | Source-data gaps (Belgium 2013/14, Scottish split, COVID season) | Correct / remove / keep and document | Keep and document; robustness variants change test Macro-F1 by at most 0.006. | Report §8.3, §18.3 | Jayamuni
D14 | Modelling | Final feature set | FS1 / FS2 / FS3 / FS4 | FS3: highest validation Macro-F1 (0.473 best model in the ablation); FS4 added nothing. | ablation_validation_results.csv | Bandara
D15 | Modelling | Class imbalance | Resampling / class weights / none | class_weight = balanced: Macro-F1 +0.08 to +0.09 and Draw F1 from about 0 to 0.27-0.34. | candidate_ranking_validation.csv; report §18.3 | Bandara
D16 | Modelling | Final model | 6 models compared on validation | Random Forest (200 trees, max_depth 6, min_samples_leaf 5, balanced): validation Macro-F1 0.492, log loss 0.983. Naive Bayes ranked lower on Macro-F1 (0.473); its log loss of 2.35 also shows unreliable probabilities. | final_model_selection.csv; report §18.2 | Bandara
D17 | Modelling | Use of the test set | Test repeatedly / test once | Frozen model scored once on 2024/25-2025/26: Macro-F1 0.473 (95% CI 0.460-0.486). | final_test_metrics.csv | Bandara
D18 | Modelling | Other model families | Stop at six models / also check MLP, HistGradientBoosting, XGBoost, AdaBoost, SVM and ordinal logistic regression | Checked after selection, on validation only: best was HistGradientBoosting at +0.00005 vs Random Forest, far below the 0.01 rule, and AdaBoost was 0.013 lower, so Random Forest stays. | additional_models_validation.csv; adaboost_validation.csv; report §18.5; Model_Choice_Justification.docx | Bandara
D19 | Project | AI assistance | Undeclared / declared and verified | Declared; every number comes from executed code. | Report §22 | All
D20 | Modelling | Classic statistical model | Machine-learning models only / also a Poisson goal model | Checked after selection, on validation only: Macro-F1 0.405 (most probable result; never predicts a draw) and 0.453 (prior-corrected) against 0.492; probabilities slightly better (log loss 0.969 against 0.983). Random Forest kept; Poisson reported as the statistical baseline. | poisson_validation.csv; report §18.8; notebook §27 | Kumara, Bandara